## Schedule
Project Schedule
Refer to the CDC_UP_Microsoft_Project_Practices_Guide.doc for template information that should be updated prior to using this template.
Project Name:
Project Manager Name:
Project Start Date:
Project Schedule Last Updated Date:
ID | Task Name | Duration |  | Baseline Start | Expected Start | Actual Start | Baseline Finish | Expected Finish | Actual Finish | Baseline Work |  | Actual Work |  | Remaining Work |  | % Complete | EAC |  | EAC Variance |  | Predecessors | Resource Names
0 | CDC UP Project Schedule Template (Example) | 33 | days | NA | 2007-01-01 08:00 | NA | NA | 2007-02-09 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
1 | Project Management Activities | 3 | days | NA | 2007-01-01 08:00 | NA | NA | 2007-01-02 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
2 | Complete Project Charter | 1 | days | NA | 2007-01-01 08:00 | NA | NA | 2007-01-01 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
3 | Complete Project Management Plan | 1 | days | NA | 2007-01-02 08:00 | NA | NA | 2007-01-02 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 2
4 | Conduct Monitoring & Controlling Activities | 1 | days | NA | 2007-01-01 08:00 | NA | NA | 2007-01-01 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
5 | UP Management Activities Completed | 0 | days | NA | 2007-01-01 08:00 | NA | NA | 2007-01-01 08:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
6 | Initiation/Planning | 3 | days | NA | 2007-01-01 08:00 | NA | NA | 2007-01-03 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
7 | Conduct Feasibility Study | 1 | days | NA | 2007-01-01 08:00 | NA | NA | 2007-01-01 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
8 | Complete Business Case | 1 | days | NA | 2007-01-02 08:00 | NA | NA | 2007-01-02 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 7
9 | Complete Project Planning | 1 | days | NA | 2007-01-03 08:00 | NA | NA | 2007-01-03 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 8
10 | Initiation/Planning Activities Completed | 0 | days | NA | 2007-01-03 17:00 | NA | NA | 2007-01-03 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 9
11 | Requirements Analysis | 2 | days | NA | 2007-01-04 08:00 | NA | NA | 2007-01-05 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
12 | Complete Requirements Gathering | 1 | days | NA | 2007-01-04 08:00 | NA | NA | 2007-01-04 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 10
13 | Complete Security Planning | 1 | days | NA | 2007-01-05 08:00 | NA | NA | 2007-01-05 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 12
14 | Requirements Analysis Completed | 0 | days | NA | 2007-01-05 17:00 | NA | NA | 2007-01-05 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 13
15 | Design | 4 | days | NA | 2007-01-08 08:00 | NA | NA | 2007-01-11 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
16 | Complete High-Level Design | 1 | days | NA | 2007-01-08 08:00 | NA | NA | 2007-01-08 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 14
17 | Complete Proof of Concept | 1 | days | NA | 2007-01-09 08:00 | NA | NA | 2007-01-09 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 16
18 | Complete Detailed Design | 1 | days | NA | 2007-01-10 08:00 | NA | NA | 2007-01-10 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 17
19 | Complete Technical Specification | 1 | days | NA | 2007-01-11 08:00 | NA | NA | 2007-01-11 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 18
20 | Design Completed | 0 | days | NA | 2007-01-11 17:00 | NA | NA | 2007-01-11 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 19
21 | Development | 8 | days | NA | 2007-01-12 08:00 | NA | NA | 2007-01-23 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
22 | Complete Build/Develop | 1 | days | NA | 2007-01-12 08:00 | NA | NA | 2007-01-12 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 20
23 | Complete Integration Planning | 1 | days | NA | 2007-01-15 08:00 | NA | NA | 2007-01-15 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 22
24 | Complete Documentation | 1 | days | NA | 2007-01-16 08:00 | NA | NA | 2007-01-16 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 23
25 | Complete Test Planning | 1 | days | NA | 2007-01-17 08:00 | NA | NA | 2007-01-17 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 24
26 | Complete Deployment Planning | 1 | days | NA | 2007-01-18 08:00 | NA | NA | 2007-01-18 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 25
27 | Complete Training Planning | 1 | days | NA | 2007-01-19 08:00 | NA | NA | 2007-01-19 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 26
28 | Complete Business Continuity Planning | 1 | days | NA | 2007-01-22 08:00 | NA | NA | 2007-01-22 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 27
29 | Complete Transition Planning | 1 | days | NA | 2007-01-23 08:00 | NA | NA | 2007-01-23 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 28
30 | Development Completed | 0 | days | NA | 2007-01-23 17:00 | NA | NA | 2007-01-23 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 29
31 | Test | 6 | days | NA | 2007-01-24 08:00 | NA | NA | 2007-01-31 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
32 | Complete Unit test | 1 | days | NA | 2007-01-24 08:00 | NA | NA | 2007-01-24 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 30
33 | Complete Function Test | 1 | days | NA | 2007-01-25 08:00 | NA | NA | 2007-01-25 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 32
34 | Complete Integration Test | 1 | days | NA | 2007-01-26 08:00 | NA | NA | 2007-01-26 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 33
35 | Complete Regression Test | 1 | days | NA | 2007-01-29 08:00 | NA | NA | 2007-01-29 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 34
36 | Complete System Test | 1 | days | NA | 2007-01-30 08:00 | NA | NA | 2007-01-30 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 35
37 | Complete User Acceptance Test | 1 | days | NA | 2007-01-31 08:00 | NA | NA | 2007-01-31 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 36
38 | Test Completed | 0 | days | NA | 2007-01-31 17:00 | NA | NA | 2007-01-31 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 37
39 | Implementation | 3 | days | NA | 2007-02-01 08:00 | NA | NA | 2007-02-05 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
40 | Complete Deployment | 1 | days | NA | 2007-02-01 08:00 | NA | NA | 2007-02-01 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 38
41 | Complete Training | 1 | days | NA | 2007-02-02 08:00 | NA | NA | 2007-02-02 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 40
42 | Complete Support | 1 | days | NA | 2007-02-05 08:00 | NA | NA | 2007-02-05 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 41
43 | Development/Implementation Completed | 0 | days | NA | 2007-02-05 17:00 | NA | NA | 2007-02-05 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 42
44 | Operations & Maintenance | 2 | days | NA | 2007-02-06 08:00 | NA | NA | 2007-02-07 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
45 | Complete Operations Activities | 1 | days | NA | 2007-02-06 08:00 | NA | NA | 2007-02-06 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 43
46 | Complete Maintenance Activities | 1 | days | NA | 2007-02-07 08:00 | NA | NA | 2007-02-07 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 45
47 | Operations & Maintenance Completed | 0 | days | NA | 2007-02-07 17:00 | NA | NA | 2007-02-07 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 46
48 | Disposition | 2 | days | NA | 2007-02-08 08:00 | NA | NA | 2007-02-09 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
49 | Complete Archive | 1 | days | NA | 2007-02-08 08:00 | NA | NA | 2007-02-08 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 47
50 | Complete Disposal | 1 | days | NA | 2007-02-09 08:00 | NA | NA | 2007-02-09 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 49
51 | Retirement Completed | 0 | days | NA | 2007-02-09 17:00 | NA | NA | 2007-02-09 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 50
52 | Project Completed | 0 | days | NA | 2007-02-09 17:00 | NA | NA | 2007-02-09 17:00 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 51
Note on A8: e: Task ID
Note on B8: e: Task Name A field in which you may type or edit information about the task to be performed.
Note on C8: e: Duration in Days A type of field whose content is expressed as a duration of time that represents the total span of active working time for a task.
Note on E8: e: Baseline Start Date The original project plans start date used to track progress on a project. The baseline is a snapshot of the schedule at the time that the schedule has been formally approved.
Note on F8: e: Expected Start Date The date when an assigned resource is scheduled to begin working on a task.
Note on G8: e: Actual Start Date The date when an assigned resource actually begins working on a task.
Note on H8: e: Baseline Finish Date The original project plans finish date used to track progress on a project. The baseline is a snapshot of the schedule at the time that the schedule has been formally approved.
Note on I8: e: Expected Finish Date The date when an assigned resource is scheduled to finish working on a task.
Note on J8: e: Actual Finish Date The date when an assigned resource actually finishes working on a task.
Note on K8: e: Baseline Work The original project plans work used to track progress on a project. The baseline is a snapshot of the schedule at the time that the schedule has been formally approved.
Note on M8: e: Actual Work The amount of work that has already been done by resources assigned to tasks.
Note on O8: e: Remaining Work The amount of time still required to complete a task.
Note on Q8: e: % Complete The current status of a task, expressed as the percentage of the task's completion.
Note on R8: e: Estimate At Complete (EAC) The total amount of time scheduled on a task at its completion for all resources assigned to that task.
Note on T8: e: Estimate At Complete (EAC) Variance The difference between baseline work for a task and its calculated EAC.
Note on V8: e: Predecessors Task IDs for tasks that must start or finish before another task can start of finish.
Note on W8: e: Resource Names The list of all resources assigned to a task.