## Duration Estimating Tool
Duration Estimating Tool
WORK BKDN | TASK TITLE | Optimistic | Most Likely | Pessimistic | tE | Standard Deviation | Continence Reserve | Planning Duration
1 | Preliminary Design | [5 empty] | 95%
1.1 | Minimum/Maximum Flow Rates | 1 | 4 | 8 | 4.1667 | 1.1667 | 2.3333 | 6.5
1.2 | Minimum/Maximum Pressures |  |  |  | 0 | 0 | 0 | 0
1.3 | Class Location |  |  |  | 0 | 0 | 0 | 0
1.4 | Redundant Operation Y/N |  |  |  | 0 | 0 | 0 | 0
1.5 | Easement Acquisition |  |  |  | 0 | 0 | 0 | 0
1.6 | Civil Survey |  |  |  | 0 | 0 | 0 | 0
1.7 | Geotechnical Survey |  |  |  | 0 | 0 | 0 | 0
1.8 | Special Exception Permit Required (Local Zoning) Y/N |  |  |  | 0 | 0 | 0 | 0
1.9 | Investigative Bell Hole for pipe depth, longitudinal and girth weld seam locations |  |  |  | 0 | 0 | 0 | 0
2 | Design Considerations | [5 empty] | 99.7%
2.1 | Hot Tap Y/N |  |  |  | 0 | 0 | 0 | 0
2.2 | Metering & Regulating: prefabricated or stick building in field. Building Y/N |  |  |  | 0 | 0 | 0 | 0
2.3 | Heater Y/N |  |  |  | 0 | 0 | 0 | 0
2.4 | Actuators controlled remotely |  |  |  | 0 | 0 | 0 | 0
2.5 | Communications requirements for SCADA, Gas Control (satellite dish / phone line / cell mode, back-up method, etc.) |  |  |  | 0 | 0 | 0 | 0
2.6 | Secuirty Requirements (fencing, gates, signs, lighting) |  |  |  | 0 | 0 | 0 | 0
2.7 | Cathodic Protection Design |  |  |  | 0 | 0 | 0 | 0
2.8 | Special Customer Requirements (gas cleanliness, comm. Lines, etc.) |  |  |  | 0 | 0 | 0 | 0
3 | Environmental | [5 empty] | 100%
3.1 | FERC - Schedule In-Service approval to meet project deadline |  |  |  | 0 | 0 | 0 | 0
3.2 | State |  |  |  | 0 | 0 | 0 | 0
3.3 | Local |  |  |  | 0 | 0 | 0 | 0
4 | Engineered Material Procurement | [5 empty] | 95%
4.1 | Filter Separator (s) |  |  |  | 0 | 0 | 0 | 0
4.2 | Meter Skid |  |  |  | 0 | 0 | 0 | 0
4.3 | Control/Regulator Skid |  |  |  | 0 | 0 | 0 | 0
4.4 | Dual Clss Dekatherm Building |  |  |  | 0 | 0 | 0 | 0
4.5 | Large Bore Vlaves |  |  |  | 0 | 0 | 0 | 0
4.6 | Actuators |  |  |  | 0 | 0 | 0 | 0
4.7 | Hot Tap Saddle (only if perfoming Hot Tap) |  |  |  | 0 | 0 | 0 | 0
4.8 | TDW Hot Tap Services (only if performing Hot Tap) |  |  |  | 0 | 0 | 0 | 0
4.9 | Heater |  |  |  | 0 | 0 | 0 | 0
5 | Material Procurement | [5 empty] | 68%
5.1 | Pipe and Fittings |  |  |  | 0 | 0 | 0 | 0
5.2 | Small Bore Valves |  |  |  | 0 | 0 | 0 | 0
5.3 | Stud Bolts, Nuts |  |  |  | 0 | 0 | 0 | 0
5.4 | Flanges, Gaskets |  |  |  | 0 | 0 | 0 | 0
5.5 | Communications Equipment (satellite dish, cell modem, etc.) |  |  |  | 0 | 0 | 0 | 0
5.6 | Cathodic Protection Materials (anodes, wires, insulating kits, etc.) |  |  |  | 0 | 0 | 0 | 0