## Slide 1
Your project is completed and you find that many of the requirements that you included did not really tie in with any particular business need. You most likely skipped over or did a poor job of creating which of the following?
  Scope Management Plan
  Project Charter
  Requirements Traceability Matrix
  Requirements Management Plan
Answer: C.
The Requirements Traceability Matrix is expressly designed to tie each requirement to a particular business need, to ensure extraneous and needless requirements are not incorporated into the project.
Notes: Answer: C.
The Requirements Traceability Matrix is expressly designed to tie each requirement to a particular business need, to ensure extraneous and needless requirements are not incorporated into the project.

## Slide 2
An office building construction project calls for a fountain to be constructed in the office lobby, however, the materials for the fountain would not fit through the door once the lobby is completed. Thus, the builder must begin installing the large fountain components before the lobby itself is completed. The relationship between these activities (constructing the fountain and building the lobby) is best described how?
  A start to finish relationship
  Fast tracking
  Lead
  Lag
Answer: A.
“Relationship” is the key word. Sequence Activates has four relationships, Start to Finish
Start to Start
Finish to Finish
Finish to Start
Notes: Answer: A.
The installation of the fountain must at least start before the construction of the lobby can be completed. This is the rarest of the dependency relationships. One way to clarify these relationships in your mind is to insert the words “in order” into the phrase, i.e. “start in order to finish.” This may help clarify the ordering of tasks in your mind.

## Slide 3
All of the following would be incorporated into the Project Management Plan except for which one?
  Project Charter
  Requirements Management Plan
  Risk Management Plan
  Schedule Management Plan
Answer: A.
B, C and D are all items that would be contained in the Project Management Plan. See p89 PMBOK
Notes: Answer: A.
B, C and D are all items that would be contained in the Project Management Plan. The Project Charter itself would not be part of the Project Management Plan.

## Slide 4
You are managing a project to install solar power panels to your company’s office buildings. Using a beta distribution from PERT, you estimate the project should take 30 days. Your pessimistic estimate is 44 days and your optimistic estimate is 20 days. You must be accurate to within a 99.73% probability. What deration estimate will you provide them?
  42 days
  40 days
  44 days
  44 days
Answer: A.
To perform this calculation, you must first establish the value of one standard deviation, so you subtract the optimistic value from the pessimistic value and divide that result by 6. Here, that gives you a standard deviation of 4. Because we need a 99.73% probability, we must allow for 3 standard deviations added to our original estimate of 30 days.
Notes: Answer: A.
To perform this calculation, you must first establish the value of one standard deviation, so you subtract the optimistic value from the pessimistic value and divide that result by 6. Here, that gives you a standard deviation of 4. Because we need a 99.73% probability, we must allow for 3 standard deviations on each side of our original estimate. In this case, that results in an 18-42 day range. Remember, one standard deviation yields a 68.26% probability, two yields a 95.44% probability, and three yields a 99.73% probability. Six standard deviations, or six sigmas, yields a 99.999% probability. You should know the probabilities for one, two, three and six standard deviation (sigmas) for the exam.

## Slide 5
Which of the following is not true regarding AOA Precedence Diagramming Method (PDM)?
  It displays the time periods on the boxes, or nodes, and the activity on the arrows connecting the nodes.
  It uses both arrows and boxes (nodes) to set forth the sequence in which activities must be performed.
  It is also called AON, or Activity on Node.
  It allows for dependency relationships other than finish to start.
Answer: A.
AOA or Activity on node PDM displays the activity in the box (or node) and the arrow indicates the dependency. Answer A describes Activity on Arrow, or Arrow Diagramming Method, which is a lesser used method that would only allow for finish to start dependencies to be shown, and which shows the activity on the arrow instead of in the node.
Notes: Answer: A.
PDM displays the activity in the box (or node) and the arrow indicates the dependency. Answer A describes Activity on Arrow, or Arrow Diagramming Method, which is a lesser used method that would only allow for finish to start dependencies to be shown, and which shows the activity on the arrow instead of in the node.

## Slide 6
A Project Statement of Work should typically contain and/or consider the following items:
  High-level product description, business need and company’s strategic plan
  High-level product description, business need and list of key stakeholders
  High-level product description and contract
  Scope statement and business need
Answer: A
These are the three items contained in the Project SOW. Note that it is important for the project manager to have some sense of the company’s big-picture strategic plan in order to be the most effective. B is wrong because the SOW need not list all key stakeholders – indeed, they may not have all been identified at this very early phase (though the PM should be working hard to identify all of them). Note the scope statement listed in (D) would not yet have been created at this early phase.
Notes: A
These are the three items contained in the Project SOW. Note that it is important for the project manager to have some sense of the company’s big-picture strategic plan in order to be the most effective. B is wrong because the SOW need not list all key stakeholders – indeed, they may not have all been identified at this very early phase (though the PM should be working hard to identify all of them). Note the scope statement listed in (D) would not yet have been created at this early phase.

## Slide 7
Which of the following would be considered an Enterprise Environmental Factor?
  Budget templates
  Lessons Learned from prior similar projects
  Company policies
  Progressive Elaboration
Answer: C.
Because A and B are not always EEFs typically they are OPAs. D is a technique used in project planning and thus is neither an EEF nor an OPA. Company culture is always an EEF.
Notes: Answer: C.
Because A and B refer to actual written documents, they are considered Organizational Process Assets. D is a technique used in project planning and thus is neither an EEF nor an OPA.

## Slide 8
Which is true regarding the project life cycle?
  As time goes by, stakeholder influence over a project increases.
  As time goes by, project risk increases along with stakeholder influence.
  As time goes by, project risk decreases.
  Costs are at their highest near the very end of the project.
Answer: C.
The opposite is true with respect to A and B. D is incorrect because costs are highest near the middle of the project, as the level of work hits its peak. This is shown using an S-curve.
Notes: Answer: C.
The opposite is true with respect to A and B. D is incorrect because costs are highest near the middle of the project, as the level of work hits its peak. This is shown using an S-curve.

## Slide 9
The project charter would most appropriately be signed by which of the following?
  The project manager
  The project manager and project team
  The project sponsor
  All stakeholders
Answer: C.
The project sponsor, being both a key stakeholder and the source of funding, would be the best person of the options listed to sign off on the project charter. The project charter should be signed by someone independent of the project team, ruling out (A) and (B). D is incorrect because, while some key stakeholders may well sign the charter, there are too many potential stakeholders for this to be feasible or useful.
Notes: Answer: C.
The project sponsor, being both a key stakeholder and the source of funding, would be the best person of the options listed to sign off on the project charter. The project charter should be signed by someone independent of the project team, ruling out (A) and (B). D is incorrect because, while some key stakeholders may well sign the charter, there are too many potential stakeholders for this to be feasible or useful.

## Slide 10
Which of the following are considered project constraints?
  Resources
  Resources and budget
  Resources, schedule and budget
  Resources and third-party contractors
Answer: C.
C is the best answer because it is the most inclusive. D is incorrect – the presence of a third-party contractor, in and of itself, should not materially limit project management options, though it could affect other constraints such as budget and scheduling. In any event, it does not incorporate the 3 very important constraints set out in C.
Notes: Answer: C.
C is the best answer because it is the most inclusive. D is incorrect – the presence of a third-party contractor, in and of itself, should not materially limit project management options, though it could affect other constraints such as budget and scheduling. In any event, it does not incorporate the 3 very important constraints set out in C.

## Slide 11
Which of the following processes is concerned with defining, coordinating and integrating the various subsidiary project plans?
  Collect Requirements
  Direct and Manage Project Work
  Develop Project Management Plan
  Monitor and Control Project Work
Answer: C.
Develop Project Management Plan involves identifying and documenting the processes which will be used to manage the project. It is the first step in the planning process, however, the outputs of later planning processes will be incorporated back into the Project Management Plan. Thus, the Project Management Plan begins as a relatively “bare-bones” document, but becomes more comprehensive as the other planning processes are completed.
Notes: Answer: C.
Develop Project Management Plan involves identifying and documenting the processes which will be used to manage the project. It is the first step in the planning process, however, the outputs of later planning processes will be incorporated back into the Project Management Plan. Thus, the Project Management Plan begins as a relatively “bare-bones” document, but becomes more comprehensive as the other planning processes are completed.

## Slide 12
You are managing a project to manufacture a new line of automobiles, with a value of $10,000 each. At the present time, you have produced 50 cars. You had planned on producing 75 cars by this time, however. What is your SPI?
  -250,000
  1.67
  .67
  You do not have enough information to calculate SPI.
Answer: C.
SPI = EV/PV, or in this case, $500,000/$750,000. Remember that for an index, you need to divide and for a variance, you would subtract.
Notes: C

## Slide 13
Which of the following is used to determine which of the processes and process groups should be performed for a specific project?
  Progressive Elaboration
  Tailoring
  Rolling Wave Planning
  Expert Judgment
Answer: B.
Determining which processes and process groups to be employed in a given project is called tailoring. In general, all five process groups should be applied to projects, though in some smaller projects, tailoring allows the project manager to bypass some processes which may not be needed. For the exam, do not assume that any processes or process groups should be bypassed, but you should know about tailoring nonetheless.
Notes: Answer: B.
Determining which processes and process groups to be employed in a given project is called tailoring. In general, all five process groups should be applied to projects, though in some smaller projects, tailoring allows the project manager to bypass some processes which may not be needed. For the exam, do not assume that any processes or process groups should be bypassed, but you should know about tailoring nonetheless.

## Slide 14
All of the following processes fall within the Project Scope Management knowledge area except for which one?
  Collect Requirements
  Validate Scope
  Define Scope
  Agile Scope Development
Answer: D.
  Agile Scope Development isn't a process in the PMBOK
Notes: Answer: D.
Develop Project Management Plan belongs to the Integration Management knowledge area, while the remaining choices all fall within scope management.

## Slide 15
You are working on the Control Schedule process. Which of the following measurements are you focusing on?
  SV and CPI
  SV and SPI
  BAC and CPI
  SV and AC
Answer: B.
Schedule Variance and Schedule Performance Index are the measurements which would be most critical to the Control Schedule process. Remember that you may only get abbreviations on the exam.
Notes: B

## Slide 16
Along with requirements documentation, the other output of the Collect Requirements process is ______?
  Stakeholder Management Plan
  Requirements Traceability Matrix
  Project Scope Statement
  WBS
Answer: B.
The outputs from Collect Requirements are the Requirements Documentation and Requirements Traceability Matrix .
Notes: Answer: B.
The two outputs from Collect Requirements are the Requirements Documentation, and the Requirements Traceability Matrix. Stakeholder Management Plan is an output from Plan Stakeholder Management; Project Scope Statement is an output from Define Scope; the WBS is an output of Create WBS.

## Slide 17
You are managing a project for an outside customer that has proceeded into the execution process group when the customer hires on a new COO. The COO comes to you and wants to get up to speed on your project. She wants to know specifically what her company will be getting when the project is complete and what work will be done in order to complete the project. The most informative document for her to review would be which of the following?
  The Project Scope Statement
  The Project Charter
  The Requirements Documentation
  The Deliverables Management Plan
Answer: A.
The Project Scope Statement would state what the desired outcomes or deliverables were, and describe what work will be done to attain them. The Project Charter would speak broadly about this, but the Scope Statement is much better defined and detailed. The Requirements Documentation would not be nearly as helpful, since it documents requirements for the final product or outcome, but does not describe the outcome itself the way the Scope Statement does. There is no Deliverables Management Plan, so D is wrong.
Notes: Answer: A.
The Project Scope Statement would state what the desired outcomes or deliverables were, and describe what work will be done to attain them. The Project Charter would speak broadly about this, but the Scope Statement is much better defined and detailed. The Requirements Documentation would not be nearly as helpful, since it documents requirements for the final product or outcome, but does not describe the outcome itself the way the Scope Statement does. There is no Deliverables Management Plan, so D is wrong.

## Slide 18
You are a project manager overseeing the development of a new software package to be unveiled at a trade show in less than nine months. You have had a couple setbacks and you are concerned that the product may not be completed in time for the trade show. The project sponsor has made it clear that the software must not only be ready, but entirely bug free, by the time of the trade show, and that budget concerns must be subordinate to those. Which of the following would be the best option in this case?
  Fast-tracking
  Crashing
  Schedule Compression
  A reduction of the project scope
Answer: B.
Crashing, or adding more resources to the project, is the appropriate response here, as time is the primary constraint and budget comes second. Fast-tracking, or performing otherwise sequential activities in parallel, would not be best here because the risk of defects increases and the product must be bug-free. Crashing is hard on the budget, but here budget is subordinate to time and quality in terms of your constraints. C is not specific enough – A and B are both methods for compressing the schedule. D could perhaps be used as a last resort, but you should clearly look to schedule compression techniques first.
Notes: Answer: B.
Crashing, or adding more resources to the project, is the appropriate response here, as time is the primary constraint and budget comes second. Fast-tracking, or performing otherwise sequential activities in parallel, would not be best here because the risk of defects increases and the product must be bug-free. Crashing is hard on the budget, but here budget is subordinate to time and quality in terms of your constraints. C is not specific enough – A and B are both methods for compressing the schedule. D could perhaps be used as a last resort, but you should clearly look to schedule compression techniques first.
- You can’t fasttrack because you’re already concerned about quality

## Slide 19
You are managing a project which involves excavation of large amounts of land. Your company owns two heavy-duty excavators but you are unsure if they will be available during the time period you will need them. You should consult which of the following?
  Resource Breakdown Structure
  Requirements Documentation
  Resource Requirements
  Resource Calendar
Answer: D.
The Resource Calendar will show which resources are available for use on your project as well as the time in which they are available. This includes both human resources and other resources as well.
Notes: Answer: D.
The Resource Calendar will show which resources are available for use on your project as well as the time in which they are available. This includes both human resources and other resources as well. Note that B and C are inapplicable here. They deal with requirements for the end-product itself, which should not be confused with things you require in order to reach the end-product.

## Slide 20
You are managing the development of a residential neighborhood comprised of 12 homes of equal cost ($200,000 each). To date, you have completed 4 homes. Your progress has been hindered by a labor strike which left you short of construction workers, however, the labor issues have been resolved and you now have all of the workers you need. By this time, you had planned to have 6 homes completed. You have spent $900,000 to complete the 4 homes. How much more money will you spend to complete the project?
  $1,500,000
  $1,600,000
  $1,800,000
  You do not have enough information to answer this question.
Answer: B
The question asks you to calculate ETC, the formula for which is EAC-AC. You must first calculate EAC, and since the facts tell you that the variances you have encountered to date are atypical, you will use AC+(BAC-EV). Here, actual costs are $900,000. BAC (original cost estimate) is $2.4 million and earned value is $800,000. Thus, your EAC is $2.5 million. Subtract from that your actual costs of $900,000 and you have your ETC of $1.6 million.
Notes: B