## Slide 1
Your project is completed and you find that many of the requirements that you included did not really tie in with any particular business need. You most likely skipped over or did a poor job of creating which of the following?
  Scope Management Plan
  Project Charter
  Requirements Traceability Matrix
  Requirements Management Plan

## Slide 2
An office building construction project calls for a fountain to be constructed in the office lobby, however, the materials for the fountain would not fit through the door once the lobby is completed. Thus, the builder must begin installing the large fountain components before the lobby itself is completed. The relationship between these activities (constructing the fountain and building the lobby) is best described how?
  A start to finish relationship
  Fast tracking
  Lead
  Lag

## Slide 3
All of the following would be incorporated into the Project Management Plan except for which one?
  Project Charter
  Requirements Management Plan
  Risk Management Plan
  Schedule Management Plan

## Slide 4
You are managing a project to install solar power panels to your company’s office buildings. Using a beta distribution from PERT, you estimate the project should take 30 days. Your pessimistic estimate is 44 days and your optimistic estimate is 20 days. You must be accurate to within a 99.73% probability. What deration estimate will you provide them?
  42 days
  40 days
  44 days
  44 days

## Slide 5
Which of the following is not true regarding AOA Precedence Diagramming Method (PDM)?
  It displays the time periods on the boxes, or nodes, and the activity on the arrows connecting the nodes.
  It uses both arrows and boxes (nodes) to set forth the sequence in which activities must be performed.
  It is also called AON, or Activity on Node.
  It allows for dependency relationships other than finish to start.

## Slide 6
A Project Statement of Work should typically contain and/or consider the following items:
  High-level product description, business need and company’s strategic plan
  High-level product description, business need and list of key stakeholders
  High-level product description and contract
  Scope statement and business need

## Slide 7
Which of the following would be considered an Enterprise Environmental Factor?
  Budget templates
  Lessons Learned from prior similar projects
  Company policies
  Progressive Elaboration

## Slide 8
Which is true regarding the project life cycle?
  As time goes by, stakeholder influence over a project increases.
  As time goes by, project risk increases along with stakeholder influence.
  As time goes by, project risk decreases.
  Costs are at their highest near the very end of the project.

## Slide 9
The project charter would most appropriately be signed by which of the following?
  The project manager
  The project manager and project team
  The project sponsor
  All stakeholders

## Slide 10
Which of the following are considered project constraints?
  Resources
  Resources and budget
  Resources, schedule and budget
  Resources and third-party contractors

## Slide 11
Which of the following processes is concerned with defining, coordinating and integrating the various subsidiary project plans?
  Collect Requirements
  Direct and Manage Project Work
  Develop Project Management Plan
  Monitor and Control Project Work

## Slide 12
You are managing a project to manufacture a new line of automobiles, with a value of $10,000 each. At the present time, you have produced 50 cars. You had planned on producing 75 cars by this time, however. What is your SPI?
  -250,000
  1.67
  .67
  You do not have enough information to calculate SPI.

## Slide 13
Which of the following is used to determine which of the processes and process groups should be performed for a specific project?
  Progressive Elaboration
  Tailoring
  Rolling Wave Planning
  Expert Judgment

## Slide 14
All of the following processes fall within the Project Scope Management knowledge area except for which one?
  Collect Requirements
  Validate Scope
  Define Scope
  Agile Scope Development

## Slide 15
You are working on the Control Schedule process. Which of the following measurements are you focusing on?
  SV and CPI
  SV and SPI
  BAC and CPI
  SV and AC

## Slide 16
Along with requirements documentation, the other output of the Collect Requirements process is ______?
  Stakeholder Management Plan
  Requirements Traceability Matrix
  Project Scope Statement
  WBS

## Slide 17
You are managing a project for an outside customer that has proceeded into the execution process group when the customer hires on a new COO. The COO comes to you and wants to get up to speed on your project. She wants to know specifically what her company will be getting when the project is complete and what work will be done in order to complete the project. The most informative document for her to review would be which of the following?
  The Project Scope Statement
  The Project Charter
  The Requirements Documentation
  The Deliverables Management Plan

## Slide 18
You are a project manager overseeing the development of a new software package to be unveiled at a trade show in less than nine months. You have had a couple setbacks and you are concerned that the product may not be completed in time for the trade show. The project sponsor has made it clear that the software must not only be ready, but entirely bug free, by the time of the trade show, and that budget concerns must be subordinate to those. Which of the following would be the best option in this case?
  Fast-tracking
  Crashing
  Schedule Compression
  A reduction of the project scope

## Slide 19
You are managing a project which involves excavation of large amounts of land. Your company owns two heavy-duty excavators but you are unsure if they will be available during the time period you will need them. You should consult which of the following?
  Resource Breakdown Structure
  Requirements Documentation
  Resource Requirements
  Resource Calendar

## Slide 20
You are managing the development of a residential neighborhood comprised of 12 homes of equal cost ($200,000 each). To date, you have completed 4 homes. Your progress has been hindered by a labor strike which left you short of construction workers, however, the labor issues have been resolved and you now have all of the workers you need. By this time, you had planned to have 6 homes completed. You have spent $900,000 to complete the 4 homes. How much more money will you spend to complete the project?
  $1,500,000
  $1,600,000
  $1,800,000
  You do not have enough information to answer this question.